## Plan
DataStage Server Build/Migration Plan created and maintained by Eric Dodson
Last updated 5/31/05
eRequest ID-016727 (SRP tied to Dave Kelton's 2005 Consolidation project), ILC claim code is LXDDAD11 RF=ID-015954
Scheduled to begin 04/01/2005 and to be completed by 05/17/2005 (6.5 weeks maximum) using 50% Eric Dodson and 50% Venkat Krishna overall
The above schedule assumes no interruptions, such as other eRequests, daily maintenance problems, or problem tickets that tend to take priority
AMS Actual Hours up-to-date through 4/24/05 for Eric and up-to-date through 4/26/05 for Venkat
Task Number | Task | Resources | AMS Estimated Hours | Status | AMS Actual Hours | Actual finish date
| Server install based on the last installation |  | 40
1 | SDC Server Setup Guidance/Participation | SDC, Eric | 0 | 100% | 0
2 | Weekly Status Meetings | SDC, Eric | 4 | 100% | 4.5
3 | Server Hardware | SDC | 0 | 100% | 0
4 | Operating System | Jason Conley (SDC) | 0 | 100% | 0
5 | Network Connectivity | AT&T (SDC) | 0 | 100% | 0
6 | Disk Connectivity | Bill Baker (SDC) | 0 | 100% | 0
7 | Disk Layout | Eric | 3 | 100% | 7
8 | Setup Disk Mount Points | Bill Baker (SDC) | 0 | 100% | 0
9 | Identify Unix IDs to Create | Eric | 2 | 100% | 0.5
10 | Create Unix IDs | Jason Conley (SDC) | 0 | 100% | 0
11 | Get a new Unix ID for Venkat | Eric | 0.5 | 100%
12 | Get root access on dlxksdstg2e | Jason Conley (SDC), Eric | 0.5 | 100% | 0 | 2005-05-09
13 | Copy sudo access | Jason Conley (SDC) | 0 | 100% | 0
14 | Test sudo access | Eric | 0.5 | 100%
15 | Oracle Clients | Tom Hand (SDC), Eric | 0 | 100% | 0 | 2005-05-25
16 | Install Oracle Clients with Utilities | Tom Hand (SDC) | 0 | 100%
17 | Get Access to Oracle tnsnames.ora | Eric | 0.5 | 100% |  | 2005-05-25
18 | Configure Oracle Clients with Utilities (copy tnsnames.ora from old server) | Tom Hand (SDC), Eric | 1 | 100%
19 | Compare kernel settings between servers | Eric | 0.5 | 100%
20 | Test Oracle Client Connections | Eric, Venkat | 1.5 | 100%
20a | Test Oracle Client Utilities (export and import) | Eric | 0.5 | 100%
21 | DB2 Client | Alan Kauf-Stern (SDC), Eric, Kelly | 0 | 100% | 0
22 | Install DB2 Client | Alan Kauf-Stern (SDC) | 0 | 100%
23 | Configure DB2 Client | Alan Kauf-Stern (SDC), Eric | 1 | 100%
24 | Compare kernel settings between servers | Eric | 0.5 | 100%
25 | Test DB2 Client Connections | Eric, Kelly | 2 | 100% | 5
26 | SequeLink ODBC Client | Eric, Venkat | 0 | 100% | 0 | 2005-05-11
27 | Review SequeLink ODBC Client Install Guide | Eric, Venkat | 0.5 | 100% |  | 2005-05-04
28 | Install SequeLink ODBC Client | Eric, Venkat | 1 | 100% |  | 2005-05-04
29 | Configure SequeLink ODBC Client | Eric, Venkat | 0.5 | 100% |  | 2005-05-10
29a | Copy sqlnkdsn.ini file from old server | Eric, Venkat | 0 | 100% |  | 2005-05-04
29b | chown dsadm:dstage on all sqlnk files | Eric, Venkat | 0 | 100% |  | 2005-05-10
30 | Test SequeLink ODBC Connections | Eric, Venkat | 1 | 100% |  | 2005-05-11
31 | DataStage Server | Eric, Venkat | 0 | 100% | 0 | 2005-05-11
32 | Obtain written permission for 3rd DataStage Server license (90 days) | Steve (Lexmark), Eric | 0.5 | 100% | 1 | 2005-04-13
33 | Review DataStage Server Install Guide | Eric, Venkat | 1 | 100% | 2
34 | Compare kernel settings between servers | Eric, Venkat | 0.5 | 100% | 0.5
35 | Install DataStage Server | Eric, Venkat | 2 | 100% | 6
35a | Install Clickpack add-on (used only by WBA) | Eric, Venkat | 0.5 | 100% | 3 | 2005-04-25
36 | Configure DataStage Server | Eric | 2 | 100% |  | 2005-05-09
37 | Copy dsenv file customizations | Venkat | 1 | 100% | 1 | 2005-04-23
38 | Activate dsenv file customizations using stop/start server | Venkat | 0.5 | 100% | 0.5 | 2005-04-23
39 | Copy uvconfig file customizations | Eric | 0.5 | 100% | 0.3 | 2005-04-23
40 | Activate uvconfig file customizations using -regen, stop/start server | Eric | 0.2 | 100% | 0.3 | 2005-04-23
40a | Create the errlog file | Eric | 0.1 | 100% | 0.3 | 2005-04-23
40b | Copy .odbc.ini file customizations | Eric | 0.3 | 100% | 0.3 | 2005-04-23
40c | Update S99ds.rc file to set umask 002 | Eric | 0.2 | 100% | 0.3 | 2005-04-23
40d | Update Inactivity Timeout to 7200 in Administrator & restart server | Eric | 0.2 | 100% | 0.3 | 2005-05-09
41 | Install DataStage Server Patches (some included in uvconfig changes above) | Eric | 1.5 | 100% | 0 | 2005-04-29
41a | set /usr/lib/lwp at beginning of LD_LIBRARY_PATH in dsenv | Eric | 0.1 | 100% | 0 | 2005-04-23
41b | dsunlock dsadm/non-root utility | Eric | 0.3 | 100% |  | 2005-04-29
41c | Printer memory segment warning patch (for future reference only) | Eric | 0 | 100% | 0 | 2005-04-23
42 | Test DataStage Server with Patches | Eric | 2 | 100% | 0 | 2005-05-02
42a | Clean up files | Eric, Venkat | 0.5 | 100% | 0.5 | 2005-04-29
42b | Remove any tar/gz/gzip files from FTP of other servers | Eric, Venkat | 0 | 100% | 0 | 2005-04-23
42c | Remove DataStage Install files under /tmp/dsinstall/unpack | Eric, Venkat | 0 | 100% | 0 | 2005-04-23
42d | Move DataStage Install log files under /tmp/dsinstall/logfiles to /dstage/app/media/logfiles, chown dsadm:dstage *, chmod 640 * | Eric, Venkat | 0 | 100% | 0 | 2005-04-23
42e | Remove ClickPack Install files under /tmp/cpinstall | Eric, Venkat | 0 | 100% | 0 | 2005-04-28
42f | Move Siebel PACK Install log files under /tmp/dssiebelinstall to /dstage/app/media/logfiles, chown dsadm:dstage *, chmod 640 * | Eric, Venkat | 0 | 100% | 0 | 2005-04-29
43 | DataStage Server Security | Eric | 0 | 100% | 0 | 2005-04-28
44 | Secure system files (uvconfig, .odbc.ini, dsenv, etc.) | Eric | 1 | 100% | 0.5 | 2005-04-23
44a | chmod 754 dsenv* | Eric | 0.1 | 100% | 0 | 2005-04-23
44b | chmod 644 uvconfig* | Eric | 0.1 | 100% | 0 | 2005-04-23
44c | chmod 644 .odbc* | Eric | 0.1 | 100% | 0 | 2005-04-23
45 | Switch to each user to update .profile | Eric, Venkat | 2 | 100% |  | 2005-05-11
46 | DataStage Maintenance Scripts | Eric, Venkat | 0 | 100% | 0 | 2005-05-02
47 | Copy Scripts from old server to new server | Eric, Venkat | 1 | 100% | 1 | 2005-04-21
48 | /dstage/app/scripts/* (dsdf, dscon, dsps, etc.) | Eric, Venkat | 0 | 100% | 0.5 | 2005-04-21
49 | Daily Disk Report | Eric, Venkat | 0 | 100% | 1 | 2005-04-21
50 | Hourly Disk Check | Eric, Venkat | 0 | 100% | 1 | 2005-04-21
51 | Every-5 Minute Disk Check | Eric, Venkat | 0 | 100% | 1 | 2005-04-21
52 | /dstage/dev/maint/* (all others) | Eric, Venkat | 0 | 100% | 0.5 | 2005-04-21
53 | Test DataStage Maintenance Scripts | Eric, Venkat | 1 | 100% |  | 2005-04-26
54 | /dstage/app/scripts/* (dsdf, dscon, dsps, etc.) | Eric, Venkat | 0 | 100% |  | 2005-04-26
55 | Daily Disk Report | Eric, Venkat | 0 | 100% |  | 2005-04-26
56 | Hourly Disk Check | Eric, Venkat | 0 | 100% |  | 2005-05-02
57 | Every-5 Minute Disk Check | Eric, Venkat | 0 | 100% |  | 2005-04-26
58 | /dstage/dev/maint/* (all others) | Eric, Venkat | 0 | 100% |  | 2005-04-26
| Siebel PACK |  | 20
59 | Review Siebel PACK Install Guide | Eric, Venkat | 4 | 100% | 0.5 | 2005-04-28
60 | Install Siebel PACK 3.0.1 (--> 3.0.2) | Eric, Venkat | 4 | 100% | 7 | 2005-04-28 | 3.0.1 had install problems so we had to install 3.0.2
61 | Install Siebel PACK 3.0.1 Patches | Eric, Venkat | 4 | N/A |  | N/A | Tenny/Atlas testing didn't uncover any problems
61a | SiebelDB.class fix for DataStage 5 | Eric, Venkat | 0 | N/A |  | N/A | Tenny/Atlas testing didn't uncover any problems
61b | SiebelDB.class fix for 10K row limit | Eric, Venkat | 0 | N/A |  | N/A | Tenny/Atlas testing didn't uncover any problems
61c | dssblbc.so fix | Eric, Venkat | 0 | N/A |  | N/A | Tenny/Atlas testing didn't uncover any problems
62 | Configure Siebel PACK | Eric, Venkat | 2.5 | 100%
62a | Install SiebelClass files | Eric, Venkat | 1 | 100% |  | 2005-05-11
63 | Test Siebel PACK with Patches | Eric, Venkat | 4 | 100% |  |  | Tenny/Atlas testing didn't uncover any problems
64 | Enter CR for Server "Go Live" on 4/22/05 (starts monitoring by Ops) | Eric, Jason Conley (SDC) | 0.5 | 100% |  | 2005-04-14
| Move Projects |  | 80
65 | Pre-Development Performance Benchmark | Eric, Venkat | 5 | 100% |  | 2005-04-25
66 | Run SRM Reports | Venkat | 0 | 100% | 4 | 2005-04-25
67 | Document SRM Results | Venkat | 0 | 100% |  | 2005-04-25
68 | Development Projects | Eric, Venkat | 48
69 | Identify All Development Projects to Move (~40) | Eric | 0 | 100% | 0.5
70 | Create Development Projects | Eric, Venkat | 0 | 100% | 6
70a | Create mount points for projects that are new since the build began (dedr, CR #500921) | Eric, Venkat | 0 | 100% |  | 2005-05-09
70b | Create projects that are new since the build began (dedr) | Eric, Venkat | 0 | 100% |  | 2005-05-11
71 | Install Siebel PACK on Projects needing it (covered under Siebel PACK section above) | Eric, Venkat | 0 | 100% | 0 | 2005-04-28
72 | Setup Security in each Project (.developer.adm, .operator.adm, uvodbc.config, data, messages, scripts, etc.) | Eric, Venkat | 0 | 100% | 14 | 2005-05-10
72a | Reset each DataStage user's password as root | Eric, Venkat | 0 | 100% |  | 2005-05-11
72b | Create a document having details for project moves | Eric, Venkat | 0 | 100% |  | 2005-05-11
72c | Get root access on dlxksdstg2e to migrate dev projects to (CR 491164) | Eric | 0 | 100% |  | 2005-04-18
72d | Get root access on dlxksdstg1e to migrate dev projects off (CR 491164) | Eric | 0 | 100% |  | 2005-04-18
72e | Get root access on lxksdstg1e to migrate dev projects off (CR 505688) | Eric | 0 | 100% |  | 2005-05-13
72f | Get root access on lxksdstg1e to migrate dev projects off (CR 511762) | Eric | 0 | 100% |  | 2005-05-25
73 | Move each project according to schedule | Eric, Venkat | 0 | 100%
74 | Notify project managers of project move schedule | Eric | 0 | 100%
75 | Disable access to old project (update .developer.adm) | Eric, Venkat | 0 | 100%
76 | Make sure jobs are not running in old project | Eric, Venkat | 0 | 100%
77 | Make sure users are not connected to old project | Eric, Venkat | 0 | 100%
78 | Make sure no locks are open in old project | Eric, Venkat | 0 | 100%
79 | Export whole project as dsadm, save a backup copy to Q: | Eric, Venkat | 0 | 100%
80 | Import whole project into new project | Eric, Venkat | 0 | 100%
81 | Indentify hash files to move | Eric, Venkat | 0 | 100% |  | 2005-05-04
82 | Binary FTP hash files to new project, preserve permissions | Eric, Venkat | 0 | 100%
82a | Run CLEAN.ACCOUNT command to define VOC pointers to hash files | Eric, Venkat | 0 | 100%
83 | Binary FTP all other non-project files (i.e. scripts, data, etc.) to new project, preserve permissions | Eric, Venkat | 0 | 100%
84 | Unit Testing (see tasks under section below) | Eric, Venkat | 0 | 100%
84a | Back out if needed | Eric, Venkat | 0 | 100%
84b | Email each DataStage user initial password with instructions | Eric, Venkat | 0 | 100%
85 | Notify project managers of project move completion | Eric, Venkat | 0 | 100%
85a | Round 1 of Development project moves: 8 mostly-idle projects, no hash files | Eric, Venkat | 0 | 100%
85.1 | dcm (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.2 | ddd (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.3 | didmon (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.4 | djpurge (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.5 | dods (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.6 | dpos (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.7 | dprc (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.8 | dtrain (IBM maintenance team) | Eric, Venkat | 0 | 100%
85b | Round 2 of Development project moves | Eric, Venkat | 0 | 100%
85.9 | darp2p (IBM maintenance team) | Eric, Venkat | 0 | 100% |  | 2005-05-12
85.1 | denvpkg (IBM) | Eric, Venkat | 0 | 100% |  | 2005-05-12
85c | Round 3 of Development project moves | Eric, Venkat | 0 | 100%
85.11 | dmanu (LXK) | Eric, Venkat | 0 | 100%
85.12 | dinterco (CCP) | Eric, Venkat | 0 | 100%
85.13 | droyalty (IBM) | Eric, Venkat | 0 | 100%
85d | Round 4 of Development project moves | Eric, Venkat | 0 | 100%
85.14 | dwba (IBM maintenance team) | Eric, Venkat | 0 | 100%
85.15 | dinv (IBM/Atos) | Eric, Venkat | 0 | 100%
85.16 | dseecom (IBM/Atos) | Eric, Venkat | 0 | 100%
85.17 | dsls (IBM/Atos) | Eric, Venkat | 0 | 100%
85e | Round 5 of Development project moves | Eric, Venkat | 0 | 100%
85.18 | dloyalty (IBM) | Eric, Venkat | 0 | 100%
85.19 | dedr (IBM) | Eric, Venkat | 0 | 100%
85.2 | dstrack (IBM) | Eric, Venkat | 0 | 100%
85f | Round 6 of Development project moves | Eric, Venkat | 0 | 100%
85.21 | debusiness (IBM/Atos) | Eric, Venkat | 0 | 100% |  | 2005-05-18
85.22 | dcpdops (IBM/Atos/Lexmark) | Eric, Venkat | 0 | 100%
85.23 | dlxkcon (IBM/Atos/Lexmark) | Eric, Venkat | 0 | 100%
85g | Round 7 of Development project moves | Eric, Venkat | 0 | 100%
85.24 | dquality (IBM/Atos) | Eric, Venkat | 0 | 100% |  |  | originally scheduled 5/17-5/18, rescheduled due to slow VPN
85.25 | dsbb (IBM/Atos) | Eric, Venkat | 0 | 100% |  | 2005-05-18 | finished 1.5-2 hours late due to slow VPN
85h | Round 8 of Development project moves | Eric, Venkat | 0 | 100%
85.26 | datlssfa (IBM/Atos) | Eric, Venkat | 0 | 100%
85.27 | datlcmmn (IBM/Atos) | Eric, Venkat | 0 | 100%
85.28 | datlscc (IBM/Atos) | Eric, Venkat | 0 | 100%
85i | Round 9 of Development project moves | Eric, Venkat | 0 | 100%
85.29 | datlsam (IBM/Atos) | Eric, Venkat | 0 | 100%
85.3 | datlsall (IBM/Atos) | Eric, Venkat | 0 | 100%
85.31 | dcctr - Remove because it's no longer needed | Eric, Venkat | 0 | 100% |  | 2005-05-16
86 | Post-Development Performance Benchmark | Eric, Venkat | 6 | 100%
87 | Run SRM Reports | Venkat | 0 | 100%
88 | Document SRM Results | Venkat | 0 | 100%
89 | Review SRM Results with Customer | Eric, Venkat, Dave, Alan, Steve | 0 |  |  | 2005-05-31
90 | Go/No Go for Test Projects decision with Customer | Eric, Venkat, Dave, Alan, Steve | 0 |  |  | 2005-05-31
90a | Remove 6 EMC DASD mount points (23 GB) from lxksdstg1e dev projects | Eric | 0
90b | atlsam (1 GB) | Eric | 0
90c | atlscc (1 GB) | Eric | 0
90d | cpdops (6 GB) | Eric | 0
90e | lxkcon (11 GB) | Eric | 0
90f | atlssfa (1 GB) | Eric | 0
90g | atlsall (3 GB) | Eric | 0
90h | Remove EMD DASD mount points from dlxksdstg2e for any dev projects that were not needed | Eric | 0
91 | Test Projects | Eric, Venkat | 20 | TBD
92 | Identify All Test Projects to Move (~20) | Eric | 0 | TBD
93 | Create Test Projects | Venkat | 0 | TBD
94 | Install Siebel PACK on Projects needing it | Eric, Venkat | 0 | TBD
95 | Setup Security in each Project (.developer.adm, .operator.adm, uvodbc.config, data, messages, scripts, etc.) | Venkat | 0 | TBD
96 | Move each project according to schedule | Eric, Venkat | 0 | TBD
97 | Notify project managers of project move schedule | Eric | 0 | TBD
98 | Disable access to old project (update .developer.adm) | Eric, Venkat | 0 | TBD
99 | Make sure jobs are not running in old project | Eric, Venkat | 0 | TBD
100 | Make sure users are not connected to old project | Eric, Venkat | 0 | TBD
101 | Make sure no locks are open in old project | Eric, Venkat | 0 | TBD
102 | Export whole project as dsadm, save a backup copy to Q: | Eric, Venkat | 0 | TBD
103 | Import whole project into new project | Eric, Venkat | 0 | TBD
104 | Indentify hash files to move | Eric, Venkat | 0 | TBD
105 | Binary FTP hash files to new project, preserve permissions | Eric, Venkat | 0 | TBD
106 | Binary FTP all other non-project files (i.e. scripts, data, etc.) to new project, preserve permissions | Eric, Venkat | 0 | TBD
107 | Unit Testing (see tasks under section below) | Eric, Venkat | 0 | TBD
108 | Notify project managers of project move completion | Eric, Venkat | 0 | TBD
109 | Release root access (requested through 5/31/05) | Eric, Jason Conley (SDC) | 1 | 100% | 0.5 | 2005-05-31
| Coordinate with PMs for the projects |  | 60
110 | Distribute list of connections for each project | Eric, Venkat | 20 | 100% |  | N/A
111 | Distribute list of IDs for each project | Eric, Venkat | 12 | 100%
112 | Document and Track Test Results | Eric, Venkat | 24 | 100% |  |  | "no news is good news"
113 | Inform PMs of their Migration Schedule | Eric, Venkat | 4 | 100%
| IGSI Coordination |  | 20
114 | Emails, Sametime chats, etc. | Eric, Venkat | 20 | 95% | 8.7
| Unit Testing (IBM) |  | 25
115 | Unit Testing (IBM) | Eric, Venkat | 0 | 100%
116 | Validate Data Source/Target Connectivity per Project | Eric, Venkat | 20 | 100%
117 | Validate 1 DataStage User ID (non-dsadm) per Project | Eric, Venkat | 5 | 100% |  | 2005-05-10
| Integration Testing (IBM, Atos, Lexmark, CCP) |  | 0 | 0%
118 | Validate Data Source Connectivity per Project | Misc. (non-project activity) | 0 | N/A | 0 | N/A
119 | Validate All User Ids per Project | Misc. (non-project activity) | 0 | N/A | 0 | N/A
120 | Execute one batch cycle per project | Misc. (non-project activity) | 0 | N/A | 0 | N/A
121 | Confirm and document performance | Misc. (non-project activity) | 0 | N/A | 0 | N/A
122 | Confirm and document job completion status | Misc. (non-project activity) | 0 | N/A | 0 | N/A
| Contingency |  | 30
123 | Planning | Eric | 0 |  | 0
124 | Estimation | Eric, Dave | 2 |  | 2
125 | Status Meetings | Eric, Dave | 2 |  | 0.5
126 | Project Planning | Eric | 4 |  | 10.5
127 | eRequester | Eric | 2 |  | 0.5
128 | Tracking Actuals | Eric | 4 |  | 1
129 | Shutdown Old Development Server 5/31-6/1 (CR 512022, confirmed with John Graul) | Eric | 0 | 50%
130 | Review status with customer | Eric | 0.5 | 50%
131 | Obtain customer final OK | Eric | 0.5 | 0%
132 | Uninstall software from old server | Eric | 0.5 | N/A |  | N/A
133 | Enter CR for Old Development Server Disconnect (CR 512022) | Eric | 0.5 | 100% | 0.5
134 | Update DataStage Help Desk documentation | Eric | 4
135 | Update DataStage Server Visio chart | Eric | 4
| Total |  | 275
| Hours by geography |  | AMS Estimated Hours | Status | AMS Actual Hours | Actual finish date
| IGSI |  | 117 |  | 150 |  | as of 5/20/05
| US |  | 158 |  | 100 |  | as of 5/20/05
| Total |  | 275 | 0%

## Migration Schedule
Migration Schedule
The migration window for each project begins at 11:30 PM on the date listed and ends at 8:00 AM the following morning.
DataStage project | Planned Migration Date | Actual Migration Date | Application | Project Manager Contacts | Developers & Other Contacts | Schedule Confirmed?
darp2p | Wed 5/11 PM | Wed 5/11 PM | Ariba P2P | Dale McMurry | Eric Dodson, Prashanto Dev | Y
denvpkg | Wed 5/11 PM | Wed 5/11 PM | Environmental Packaging | Dale McMurry | Eric Dodson, Prashanto Dev, Arindam Sarkar | Y
dmanu | Thu 5/12 PM | Thu 5/12 PM | Manugistics | Jikael Merlet | Jikael Merlet | Y: 5/11 Jikael & Philippe, project is empty
dinterco | Thu 5/12 PM | Thu 5/12 PM | InterCompany Automation | Coby Hymes | Coby Hymes | Y: 5/11 Coby, running jobs on demand during the day
droyalty | Thu 5/12 PM | Thu 5/12 PM | Royalty | Dale McMurry | Balananda Bandaru | Y
dwba | Sun 5/15 PM | Sun 5/15 PM | Web Business Analyzer | Dale McMurry | Eric Dodson, Prashanto Dev | Y
dinv | Sun 5/15 PM | Sun 5/15 PM | Inventory | Dale McMurry | Eric Dodson, Prashanto Dev, Gene Howell | Y
dseecom | Sun 5/15 PM | Sun 5/15 PM | SeeCommerce | Todd Sills | Richard Iru | N: emailed Todd and Richard 5/11pm (no response)
dsls | Sun 5/15 PM | Mon 5/16 Evening | Sales Orders | Dale McMurry | Eric Dodson, Prashanto Dev, Gene Howell | Y
dloyalty | Mon 5/16 Evening | Mon 5/16 Evening | Loyalty | Terry McIlvoy | Balananda Bandaru | Y: 5/12 Balu
dedr | Mon 5/16 AM | Mon 5/16 Evening | Enterprise Data Repository | Dave Kelton | Jibanendu Acharya | Y: 5/11 Jibanendu Acharya, Dave OK during day also
dstrack | Mon 5/16 AM | Mon 5/16 Evening | Sales Tracking | Dave Kelton | Jibanendu Acharya | Y: 5/11 Dave, Jib: batch runs 4:00am-~7:00am
dlxkcon | Mon 5/16 PM | Mon 5/16 PM | Lexmark Connect | Philippe Royer | Srinivas Parsi | Y: 5/11 Philippe
dcctr | N/A - To be removed | Removed Mon 5/16 | Old Atlas Call Center | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | N/A: 5/11 Tenny, remove this one
dsbb | Tue 5/17 PM | Tue 5/17 PM | Jabil Sell Buy Back | James Dohrenwend 513-698-7092 | Srinivas Poodari, Bhusan Satapathy, Gene Howell, Renee Driscoll | Y: 5/11 James
debusiness | Tue 5/17 PM | Tue 5/17 PM | eBusiness | Creighton Medley | Creighton Medley | Y: 5/11 project is empty
datlssfa | Wed 5/18 PM | Wed 5/18 PM | Atlas SFA | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | Y: 5/11 Tenny, OK to move any time
datlcmmn | Wed 5/18 PM | Wed 5/18 PM | Atlas Common Dimensions | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | Y: 5/11 Tenny, OK to move any time
datlscc | Wed 5/18 PM | Wed 5/18 PM | Atlas Call Center | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | Y: 5/11 Tenny, OK to move any time
datlsam | Tue 5/24 PM | Tue 5/24 PM | Atlas Asset Management | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | Y: 5/11 Tenny, OK to export after 4:00pm but Eric to call first
dquality | Wed 5/25 PM | Wed 5/25 PM - Thu 5/26 | Product Quality Performance | Gene Howell (Atos), Todd Sills (IBM) | Bhusan Satapathy,Renne Driscoll | Y: 5/18 Gene, Wed night 5/25 is OK, any time after 1:30pm 5/25. The project is working out of QA/Test now.
dcpdops | Wed 5/25 PM | Thu 5/26 PM | CPD Operations | Stephan Ketcham, Dave Kelton, Dale McMurry | Tim Koliada, Steve Cornett, Prashanto Dev, Carol Young, Chris Ferraro, Hector F Garcia, Shriram Subramanian | Y: 5/17 Stephan, no active developers, during day or night is OK
datlsall | Tue 5/24 PM | Thu 5/26 PM | Atlas Integration | Ken Hill | Tennyson Modiselle, Srinivas Poodari, Luen Lin, Tim Koliada | Y: 5/11 Tenny, OK to export after 4:00pm

## Issues
Issues
Number | Opened | Closed | Impact | Issue | Status
1 | 2005-03-28 | N/A | Effort - extra US hours | DB2 AS/400 connection doesn't work, this DB2 client version is no longer supported by IBM | Need to determine the impact and inform Lexmark. Plan should be to upgrade the DB2 client as normal maintenance after this project is completed, and then troubleshoot the connection if the problem still exists using the new DB2 client.
2 | 2005-04-04 | 2005-04-11 | Schedule - 1 week | Project start date scheduled by PM(s) overlapped pre-planned vacation (Eric - 1 week) | Venkat couldn't start without anyone giving step by step directions, so project couldn't start when PM(s) scheduled it to.
3 | 2005-04-07 | 2005-04-13 | Minimal | Eric requested that Lexmark obtain a 90 day temporary DataStage license from Ascential | Received written OK on 04/13/2005 to start now plus a 60 day temporary license from Ascential, Mark Stutler, is on the way.
4 | 2005-04-12 | 2005-04-12 | Schedule - 1 day | Royalties PR took Eric's scheduled 4 hours for the project and subsequently took lost a day of Venkat's project time. | PR closed on 4/12
5 | 2005-04-14 | 2005-04-14 | Schedule - 1 day | Atlas SRP took priority (temp #1), had to cover for the IGSI holiday to ensure it would get promoted OK. | Atlas SRP work done 4/14
6 | 2005-04-21 | 2005-04-25 | Minimal | Venkat reported maintenance script errors on disk report/cron | Seems to be a mailx configuration problem, mail is not going through. Reported to Jason Conley who fixed the mailx configuration.
7 | 2005-04-22 | 2005-04-28 | Minimal | Venkat reported Siebel PACK install script hangs half way through, tried the install 4 times | Suggested Venkat try to download release 3.0.2 from Ascential and install it instead. Apparently the download access is restricted. Eric download it instead and emailed it to Venkat to try. The new Install routine was better but still had bugs in not showing the first 9 projects.
8 | 2005-04-27 | 2005-04-27 | Schedule - 1 day | Lexmark Connect and other enhancements took temp #1 priority | no project work done on 4/27
9 | 2005-04-28 | 2005-04-28 | Schedule - 1 day | Eric met with Dave and Alan to look at PCR options of moving to DataStage 7.5.1A… took all afternoon (meeting, calling Ascential, making a chart, emails) | no project work done on 4/28
10 | 2005-05-15 | N/A | Effort - extra US hours & Schedule - 1 day | Lexmark VPN is unreliable. Connection terminates during DataStage exports and imports, causing problems and delays | Affected dinv Inventory project move
11 | 2005-05-16 | N/A | Effort - extra US hours & Schedule - 1 day | Slow Lexmark VPN: dlxkcon delayed by about 2 hours, developer was delayed | Completed about 2 hours late
12 | 2005-05-17 | N/A | Effort - extra US hours & Schedule - 1 day | Lexmark VPN dcpdops full export 22 minutes on site vs. India 7+ hours | Rescheduled with export/import done in US
13 | 2005-05-18 | N/A | Effort - extra US hours & Schedule - 1 week | Lexmark VPN: dquality move rescheduled for 5/25 | Developers couldn't risk another move until 5/25, slow VPN forced US to do the export/import process
14 | 2005-05-19 | 2005-05-20 | Schedule - 2 days | Eric pulled off this project to help with CPD OPS Production Data Problems - 2 days (Steve/Roshni/Joe) | Spent 2 full days in DW Lab on CPD OPS, temporary #1 priority
15 | 2005-05-23 | N/A | Effort - extra US hours & Schedule - 1 day | Lexmark VPN: datlsall move rescheduled due to export too slow | Rescheduled with export/import done in US
16 | 2005-05-26 | 2005-05-26 | Effort - extra US hours | dquality disk usage grew beyond what the 15 GB allocated for it originally, when its usage was only around 8 GB | 5/19 Eric emailed Gene,Todd to inform them of the problem that dquality had grown to 13 GB, asked if mount point needed to be increased from 15 GB but got no response. 5/26 talked to Gene when we discovered dquality had grown past 15 GB and it wouldn't fit onto the new server. Gene deleted old data files. Eric cleared a 2 GB log file. Eric had to finish the project move instead of Venkat.